## Slide 1
Executive Summary
Smart Office
A reliable way to reserve desks and parking, reclaim unused capacity, and manage workplace policies.
Our offer
A 10-week evidence-led PoC within a 26-week full delivery program.
436 person-days · €800 per day
Notes: Sources: context/smart-office-context.md §§2–4; design/smart-office-hld.md §§2–3; poc/smart-office-poc-selection.md §4; projects/smart-office-phases-and-milestones.md; projects/smart-office-team-cost-estimate.md. Image is AI-generated illustrative art, not a photograph of the client's office. Proposal status: architecture and PoC selection are approved documents; no PoC implementation evidence exists in the repository.

## Slide 2
Client challenge and success
A single office starts the journey; the solution must also work across offices.
SMART OFFICE | CLIENT PROPOSAL
02
Employees
Find a desk or parking space for a working day and trust that a confirmed booking is theirs.
Workplace teams
Recover unused reservations after the local check-in deadline and explain every exception.
Facilities and IT
See capacity and no-shows, apply local policy, and support at least 5,000 users without redesign.
Success measures for the pilot
Zero double bookings in race tests. Safe repeat release. Late check-ins flagged. Usage and no-show baselines agreed with the client.
Notes: Sources: context/smart-office-context.md §§2–4, 6, 8–9; design/smart-office-hld.md §§12, 15. The listed technical checks are acceptance goals, not observed PoC results. Business outcome targets beyond baseline measures require client agreement.

## Slide 3
Proposed full solution
One employee journey, supported by administration and clear operating rules.
SMART OFFICE | CLIENT PROPOSAL
03
EMPLOYEE
Search
Available desks and parking for a date
Reserve
One desk and one parking booking per day
Check in
App or approved evidence source
Stay informed
Confirmation, reminder and release notice
WORKPLACE ADMINISTRATION
Manage resources and office policies
Resolve exceptions with a mandatory reason and audit trail
View bookings, check-ins, releases and no-shows
Multi-office rules use each office's local time zone; the same core platform can serve future sites.
Notes: Sources: context/smart-office-context.md §§3–8; design/smart-office-hld.md §§3–5, 10, 15. Notification delivery has an accepted at-least-once limit; avoid promising exactly-once external messages.

## Slide 4
Architecture for full delivery
A modular monolith keeps booking transactions consistent and integration boundaries clear.
SMART OFFICE | CLIENT PROPOSAL
04
Employee + admin app
Responsive web experience
Check-in providers
Authenticated ingress; vendor adapters
Smart Office API
Booking · Resource and policy
Check-in gateway · Release engine
Notifications · Audit
Office scope · Admin and reporting
Relational database
Booking constraints, state and outbox
Managed queue
Retryable check-in processing
Entra ID validates identity • Microsoft Graph sends Teams or email notices
Server-side authorization, minimum data, audit, CI security gates, backups and monitored release jobs
Notes: Sources: design/smart-office-hld.md §§2–4, 7–12. Azure is proposed, pending client ratification N-01. Database may be PostgreSQL or Azure SQL. Notification intent is unique; external delivery is at-least-once. HLD Q-01, Q-07–Q-09 affect final sizing and recovery cost.

## Slide 5
PoC scope and validation goals
Three selected capabilities test the design's highest-risk claims.
SMART OFFICE | CLIENT PROPOSAL
05
C1 Booking creation
A real database constraint rejects simultaneous resource and employee conflicts.
Proof: repeated two-request races produce one success and one clear rejection.
C2 Automatic release
Duplicate or late check-in evidence cannot create a second effect or revive a released booking.
Proof: repeat sweeps are safe, capacity reappears, and a second simulated adapter is additive.
C3 Notification dispatch
A transactional outbox records one intent; a failing channel cannot break the booking or release.
Proof: crash and retry tests show the narrow possible duplicate-send window.
PoC integrations use synthetic data and simulated Entra, Graph and check-in sources. Real tenant and hardware integration belong to full delivery.
Notes: Sources: poc/smart-office-poc-selection.md §§2–6; context/smart-office-context.md C-01, C-03, C-04; design/smart-office-hld.md §17. Selected functionalities C1–C3 are approved. Tests/results are planned, not yet achieved.

## Slide 6
PoC status and learning gate
The proof plan is approved. Implementation results are still to be generated.
SMART OFFICE | CLIENT PROPOSAL
06
What is established today
Approved requirements context
Approved full-solution HLD
Approved three-function PoC selection
Defined acceptance evidence and W10 review
What W10 must show
Real database race tests pass
Release and late-event tests pass
Outbox failure behavior is understood
Client and team accept remaining trade-offs
Planned agentic PoC lifecycle
Agents prepare bounded changes and test scaffolding; engineers review every change. CI runs security and integration checks. A human accepts PoC evidence.
Notes: Sources: poc/smart-office-poc-selection.md status and §§4–8; projects/smart-office-phases-and-milestones.md W10 gate; context/smart-office-context.md C-05–C-07; design/smart-office-hld.md §§8, 11–12. No implementation code or PoC test results were present in the repository at authoring time. Therefore this slide states planned results rather than claims success.

## Slide 7
Agentic SDLC for full delivery
Agents do bounded lifecycle work; people keep design, quality and release accountability.
SMART OFFICE | CLIENT PROPOSAL
07
01
Plan and decide
Architect and client owners resolve policy, provider and recovery choices. Agents draft designs and tasks.
02
Build and review
Agents implement scoped changes. Senior engineers review module boundaries, data migrations and authorization.
03
Prove and secure
CI runs domain, real-database concurrency, contract, security and accessibility checks. QA reviews evidence.
04
Release and operate
Human approval gates production. Operators monitor jobs, restore drills and incidents; agents assist under scoped access.
Notes: Sources: context/smart-office-context.md NFR-10–NFR-13, C-05–C-07; design/smart-office-hld.md §§8, 11–12; projects/smart-office-phases-and-milestones.md Agentic SDLC assessment. Approved tools only; least-privilege credentials, no secrets/PII in prompts, retained scan/review evidence, and human production approval.

## Slide 8
Roadmap and team
Ten weeks to a PoC decision; 26 weeks to a controlled release.
SMART OFFICE | CLIENT PROPOSAL
08
W1–W2
Setup and decisions
32 PD
W3–W10
Selected PoC
119 PD
W11–W23
Production build
215 PD
W21–W26
Hardening and release
70 PD
W10 PoC acceptance
W16 Core contracts
W26 Human-approved release
Delivery team
Principal cloud architect, senior-led backend team, frontend, platform, QA, UX, security and delivery lead.
436 PD total • 3.4 average full-time equivalents • roughly five active contributors at overlap peaks
Notes: Sources: projects/smart-office-phases-and-milestones.md six-month timeline and role matrix. Phase 0=32 PD; phases 1–3=119 PD; phases 4–5=215 PD; phase 6=70 PD. Phases 5 and 6 overlap, so the horizontal sequence is a planning summary, not a strictly sequential Gantt. Client inputs are due for Q-01/Q-04/Q-07–Q-09/Q-11 and N-01.

## Slide 9
Commercial proposal
Six-month implementation budget based on €800 per person-day.
SMART OFFICE | CLIENT PROPOSAL
09
Team baseline
436 PD
€348,800
Team reserve
20% labor reserve
€69,760
Team budget
With reserve
€418,560
Azure build infrastructure
26-week allowance
€876–€2,629
Priced planning budget
Team with reserve + Azure
€419,436–€421,189
Third-party costs stay separate from team labor. Azure uses a 23 Sep 2026 planning FX rate; AI tooling, new licenses and the real check-in vendor need quotes.
Notes: Sources: projects/smart-office-team-cost-estimate.md; projects/smart-office-third-party-cost-estimate.md; https://www.banque-france.fr/en/statistics/rates-and-prices/exchange-rates-daily-parities-2026-09-23. Rate €800/PD is client-directed planning assumption. Azure allowance is USD 1,000–3,000 converted at EUR 1 = USD 1.1411. The priced planning budget is not an all-in ceiling because agent tooling, new Microsoft licenses, check-in vendor, and optional enterprise networking/support are unquoted.

## Slide 10
Risks, assumptions and next step
The decisions below turn a sound design into a firm delivery commitment.
SMART OFFICE | CLIENT PROPOSAL
10
Usage and recovery
Client confirms peak demand, retention, availability and RTO/RPO before final sizing.
Integration choices
Workplace owner selects the first check-in provider; product owner selects Teams, email or both.
Identity and policy
Identity owner decides leaver/role changes. Workplace owner confirms same-day rebooking and cancellation rules.
Delivery access
Client confirms approved agent tools, scoped access and the Entra sandbox for production integration.
Recommended next step
Hold a joint kickoff workshop, name decision owners and authorize Phase 0. Review PoC evidence at W10 before committing the production build.
Notes: Sources: projects/smart-office-risks-and-assumptions.md §§1–4; design/smart-office-hld.md §16; poc/smart-office-poc-selection.md §6; projects/smart-office-phases-and-milestones.md; projects/smart-office-third-party-cost-estimate.md. Latest risk register commit 8673d5f adds owner and gate detail; it does not change the approved HLD, PoC selection, schedule or cost. Azure is a proposed cloud choice requiring ratification. W10 PoC evidence must be reviewed before committing production implementation.