## Slide 1
Executive Summary
Smart Office
One office serves about 200 employees with 150 desks and 30 parking spaces. Some bookings go unused.
The proposal
Booking, check-in and automatic release free unused space. A 10-week proof tests the core. AI assistants help build the solution. Three PoC capabilities already available.
26 weeks, 389 person-days. Priced items total €313,829; other costs need quotes.
Notes: Sources: context/smart-office-context.md; design/smart-office-hld.md; poc/smart-office-poc-selection.md; projects/smart-office-ai-assisted-consolidated-role-assessment.md. Image is AI-generated illustrative art. AI assistants support development of the three selected PoC capabilities. Engineers review the resulting work and tests.

## Slide 2
Client challenge and success
Initial office: about 200 employees. Proposed targets need client validation.
SMART OFFICE | CLIENT PROPOSAL
02
Unused bookings
Baseline: booked resources unused after deadline. Proposed goal: 20% fewer unclaimed desk and parking days by month 3 of pilot.
Booking speed
Baseline: median time from search to confirmation. Proposed goal: 60 seconds or less for a standard reservation.
Operational effort
Baseline: manual time spent resolving no-shows and conflicts. Proposed goal: 25% less weekly handling time.
MEASUREMENT
Compare booking, check-in and release logs with a four-week baseline; time representative user tasks; record facilities effort weekly.
Notes: Sources: context/smart-office-context.md, especially initial scale and workplace problems; review/findings-1.txt gap 4. All three numerical targets are proposal assumptions, not measured outcomes. Confirm baseline period, desk/parking denominator and pilot cohort with the client before contract acceptance.

## Slide 3
Solution concept
User journeys, core capabilities and differentiators.
SMART OFFICE | CLIENT PROPOSAL
03
01
Employee booking
Employees sign in with corporate identity, search by date, then book or cancel a desk, parking space or both.
02
Arrival and release
Check-in confirms use. Unclaimed bookings release after the local deadline so colleagues can reserve the space.
03
Workplace control
Admins set resources and local policies, resolve exceptions with an audit trail, and monitor no-shows.
Differentiators
Database constraints prevent double bookings. Notifications keep employees informed. Provider-neutral check-in and local policies support more offices.
Notes: Sources: context/smart-office-context.md §§4, 6, 8 and 9; design/smart-office-hld.md §§2, 3, 5, 7, 8 and 10. This slide describes the proposed full solution, not the current PoC scope. Initial check-in method and notification channel remain client decisions.

## Slide 4
Architecture for full delivery
A modular monolith protects booking consistency and keeps providers replaceable.
SMART OFFICE | CLIENT PROPOSAL
04
Employee + admin app
Responsive web experience
Check-in providers
Authenticated ingress and adapters
Smart Office API
Booking and resource policy
Check-in gateway and release engine
Notification outbox and audit
Office scope and reporting
Relational database
Constraints, state and outbox
Managed queue
Retryable check-in events
Entra ID for identity; Microsoft Graph for Teams or email after client choice
Server authorization, minimum data, audit, security checks, backups and monitored release jobs
Notes: Source: design/smart-office-hld.md. Azure, PostgreSQL versus Azure SQL, check-in provider and notification channel remain client decisions. The boxes show target architecture rather than current implementation status.

## Slide 5
PoC scope and validation goals
Three selected capabilities cover the core workplace journey and its main technical risks.
SMART OFFICE | CLIENT PROPOSAL
05
C1 Booking creation
Employees reserve a desk or parking space. Database constraints prevent overlapping resource bookings and daily-limit conflicts.
Validates transaction safety and clear conflict feedback.
C2 Automatic release
Arrival evidence comes from the app or a simulated provider. A missed local deadline releases unused capacity for another employee.
Validates time-zone policy, duplicate events and safe repeat release.
C3 Notifications
Confirmation, reminder and release messages are recorded as durable intents, then delivered through a replaceable channel adapter.
Validates reliable dispatch, retries and channel independence.
Demonstration story
Reserve → no arrival → release → availability returns → notice queued
Notes: Sources: poc/smart-office-poc-selection.md; design/smart-office-hld.md. The PoC scope uses synthetic data and simulated identity, notification and check-in provider boundaries; real tenant and physical provider integration are full-delivery decisions. This slide describes intended scope and validation goals, not implementation results.

## Slide 6
How we deliver with AI assistance
People guide decisions while AI assistants support focused work throughout delivery.
SMART OFFICE | CLIENT PROPOSAL
06
01
Understand and agree
Client owners confirm priorities and office rules. A team lead agrees the plan before work begins.
02
Build and check
AI assistants help build features in manageable steps. Engineers review changes and check quality, security and privacy.
03
Approve and release
The team resolves issues and confirms the agreed goals. The client owner approves the release.
04
Operate and improve
The team monitors the service and responds to defects. Feedback improves the solution and future delivery work.
Notes: Sources: agentic-workflow/protocols/lifecycle.md; bid/agentic_sdlc_proposal_team_brief.md; design/smart-office-hld.md. This combines the present delivery approach with the proposed full-delivery lifecycle. AI assistance supports bounded work while named people retain planning, review, acceptance and operating accountability. No productivity uplift is asserted.

## Slide 7
Decisions and delivery dependencies
Client choices and proof of the core journey shape the final scope and cost.
SMART OFFICE | CLIENT PROPOSAL
07
Usage and value
Confirm baseline demand, no-show rate and target economics for the first 200 employees.
Integration choice
Select first check-in provider and notice channel; obtain vendor and license quotes.
Service level
Approve cloud, retention, security, peak load and recovery requirements before sizing.
PoC evidence
Complete the release and outbox work; demonstrate the full no-show journey and record results.
Notes: Sources: review/findings-1.txt; projects/smart-office-risks-and-assumptions.md; design/smart-office-hld.md; bid/client-inputs-and-dependencies.md. Release and notification evidence and vendor costs require confirmation before commitment.

## Slide 8
Roadmap and gates
The 389-PD scenario retains the W10 proof and W26 release targets.
SMART OFFICE | CLIENT PROPOSAL
08
W1–W2
Decisions and setup
26 PD · €20,800
Policy, provider and baseline decisions
W3–W10
Client validation
109 PD · €87,200
Complete C1–C3 proof and client gate
W11–W23
Production build
194 PD · €155,200
Identity, admin and integrations
W21–W26
Release and handover
60 PD · €48,000
Load, recovery and adoption
W10 continuation gate
Proceed after three-function evidence, agreed metrics and integration quotes; rebaseline the remaining 254 PD if scope changes.
Notes: Source: projects/smart-office-ai-assisted-consolidated-role-assessment.md. Phases 0–3 total 135 PD and €108,000; phases 4–6 total 254 PD and €203,200. Phase weeks overlap. W10 and W26 are planning targets subject to capacity and client decisions.

## Slide 9
Proposed team structure
389 person-days across 26 weeks; combined leadership and part-time QA are planning assumptions.
SMART OFFICE | CLIENT PROPOSAL
09
Role | PD | Staffing model
Architect + delivery lead | 58 | One person owns design, planning and gates
Backend engineers | 135 | At least two; senior-led review and delivery
Frontend engineer | 55 | Employee and admin journeys
Platform / DevOps | 56 | CI, environments, operations and recovery
QA engineer | 44 | Part-time; risk-based checks at key gates
UX / accessibility | 12 | Usability and accessibility reviews
Security / privacy | 29 | Access, privacy and release risk reviews
Total | 389 | About 3.0 average delivery FTE
Notes: Source: projects/smart-office-ai-assisted-consolidated-role-assessment.md. This alternative staffing scenario combines architect and delivery lead in one person (58 PD) and assigns part-time QA 44 PD. The 389-PD baseline averages about 3.0 delivery FTE over 26 weeks. Engineers still review AI-generated work; client owners retain acceptance and production approval.

## Slide 10
Commercial proposal
26-week target, with 389 person-days as the working baseline and €800 per PD as the planning rate.
SMART OFFICE | CLIENT PROPOSAL
10
Team budget
389 PD
€311,200
Azure third party
26-week estimate
€876–€2,629
Priced items total
Team budget plus Azure
€312,076–€313,829
The team budget uses the 389-PD working baseline at €800 per person-day.
Other third-party costs require quotes: agent tools, any extra Microsoft licenses, the real check-in vendor and optional enterprise network or support.
For 200 employees, value depends on verified capacity savings and future office reuse. This range covers priced items only; it is not an all-in ceiling.
Notes: Sources: projects/smart-office-ai-assisted-consolidated-role-assessment.md; projects/smart-office-third-party-cost-estimate.md. The 389-PD working baseline is €311,200 at €800/PD. Azure remains €876–€2,629, giving a priced-items total of €312,076–€313,829. Excludes tax. Unquoted third-party costs are outside the priced-items range.