## Slide 1
Executive Summary
Smart Office
A simple way to plan office days and make better use of shared space.
A better office day
Employees can find and reserve the right desk or parking space before they arrive.
Workplace teams can return unused bookings to colleagues and see how the office is used.
Notes: Sources: context/smart-office-context.md; design/smart-office-hld.md; poc/smart-office-poc-selection.md. Image is AI-generated illustrative art. This slide describes the proposed user experience and intended value.

## Slide 2
Client challenge and success
Initial office: about 200 employees. Proposed targets need client validation.
SMART OFFICE | CLIENT PROPOSAL
02
Unused bookings
Baseline: booked resources unused after deadline. Proposed goal: 20% fewer unclaimed desk and parking days by month 3 of pilot.
Booking speed
Baseline: median time from search to confirmation. Proposed goal: 60 seconds or less for a standard reservation.
Operational effort
Baseline: manual time spent resolving no-shows and conflicts. Proposed goal: 25% less weekly handling time.
MEASUREMENT
Compare booking, check-in and release logs with a four-week baseline; time representative user tasks; record facilities effort weekly.
Notes: Sources: context/smart-office-context.md, especially initial scale and workplace problems; review/findings-1.txt gap 4. All three numerical targets are proposal assumptions, not measured outcomes. Confirm baseline period, desk/parking denominator and pilot cohort with the client before contract acceptance.

## Slide 3
Proposed full solution
One employee journey, with clear rules for workplace administrators.
SMART OFFICE | CLIENT PROPOSAL
03
EMPLOYEE
Search
Find available desks or parking for a date
Reserve
One booking per resource type per day
Check in
Use the app or approved provider evidence
Stay informed
Receive booking, reminder and release notices
WORKPLACE ADMINISTRATION
Manage resources and local policies
Review exceptions with reason and audit trail
See utilization, no-shows and released capacity
Architecture supports additional offices and at least 5,000 users after load validation.
Notes: Sources: context/smart-office-context.md; design/smart-office-hld.md. The 5,000-user figure is a design floor, not an observed load-test result.

## Slide 4
Architecture for full delivery
A modular monolith protects booking consistency and keeps providers replaceable.
SMART OFFICE | CLIENT PROPOSAL
04
Employee + admin app
Responsive web experience
Check-in providers
Authenticated ingress and adapters
Smart Office API
Booking and resource policy
Check-in gateway and release engine
Notification outbox and audit
Office scope and reporting
Relational database
Constraints, state and outbox
Managed queue
Retryable check-in events
Entra ID for identity; Microsoft Graph for Teams or email after client choice
Server authorization, minimum data, audit, security checks, backups and monitored release jobs
Notes: Source: design/smart-office-hld.md. Azure, PostgreSQL versus Azure SQL, check-in provider and notification channel remain client decisions. The boxes show target architecture rather than current implementation status.

## Slide 5
PoC scope and validation goals
Three selected capabilities cover the core workplace journey and its main technical risks.
SMART OFFICE | CLIENT PROPOSAL
05
C1 Booking creation
Employees reserve a desk or parking space. Database constraints prevent overlapping resource bookings and daily-limit conflicts.
Validates transaction safety and clear conflict feedback.
C2 Automatic release
Arrival evidence comes from the app or a simulated provider. A missed local deadline releases unused capacity for another employee.
Validates time-zone policy, duplicate events and safe repeat release.
C3 Notifications
Confirmation, reminder and release messages are recorded as durable intents, then delivered through a replaceable channel adapter.
Validates reliable dispatch, retries and channel independence.
Demonstration story
Reserve → no arrival → release → availability returns → notice queued
Notes: Sources: poc/smart-office-poc-selection.md; design/smart-office-hld.md. The PoC scope uses synthetic data and simulated identity, notification and check-in provider boundaries; real tenant and physical provider integration are full-delivery decisions. This slide describes intended scope and validation goals, not implementation results.

## Slide 6
How we deliver with AI assistance
People guide key decisions while AI assistants support focused delivery work.
SMART OFFICE | CLIENT PROPOSAL
06
01
Understand needs
Client priorities and office rules guide each piece of work.
02
Agree the plan
A team lead confirms scope and approach before work begins.
03
Build in steps
AI assistants help engineers create focused changes.
04
Check quality
Engineers review the work alongside automated checks.
05
Accept the result
Client and team owners decide when the outcome is ready.
Our team uses AI assistance to develop the three PoC features: booking, automatic release and employee notifications.
Notes: Sources: agentic-workflow/protocols/lifecycle.md; poc/smart-office-poc-selection.md; src/modules/booking; planning/tasks/TASK-09-release-engine.md; planning/tasks/TASK-11-notification-outbox.md. The sentence describes AI assistance across the selected PoC development scope and does not claim that all three features are complete. Engineers retain review and acceptance responsibility.

## Slide 7
Agentic SDLC for full delivery
A clear path from agreed needs to a dependable service, with people accountable at every step.
SMART OFFICE | CLIENT PROPOSAL
07
01
Before implementation
Work with client owners to confirm priorities and office rules, then agree the plan before development starts.
02
During implementation
Our team builds the agreed features in manageable steps, reviews each change and checks that it works safely for employees.
03
Before release
We resolve remaining issues, confirm the solution meets the agreed goals and ask the client owner to approve the release.
04
In production
Monitor jobs, defects and data quality. Feed incidents and failed agent evaluations into rules and regression cases.
Notes: Sources: agentic-workflow/protocols/lifecycle.md; bid/agentic_sdlc_proposal_team_brief.md; design/smart-office-hld.md. These persistence, CI, observability and defect-feedback measures are proposed additions for full delivery, not observed current controls.

## Slide 8
Roadmap and team
Each gate releases value and limits commitment before the next stage.
SMART OFFICE | CLIENT PROPOSAL
08
W1–W2
Decisions and setup
32 PD · €25,600
Policy, provider and baseline decisions
W3–W10
Client validation
119 PD · €95,200
Complete C1–C3 proof and client gate
W11–W23
Production build
215 PD · €172,000
Identity, admin and integrations
W21–W26
Release and handover
70 PD · €56,000
Load, recovery and adoption
W10 continuation gate
Proceed after three-function evidence, agreed metrics and integration quotes; reprice the remaining 285 PD if scope changes.
Team: principal cloud architect; senior-led backend; senior frontend, platform, QA, UX, security and delivery lead. Client owners join decisions and acceptance.
Notes: Sources: projects/smart-office-phases-and-milestones.md; projects/smart-office-team-cost-estimate.md. Phase 5 overlaps phase 6. W1-W10 total is 151 PD and €120,800. W11-W26 total is 285 PD and €228,000.

## Slide 9
Commercial proposal
26 weeks, 436 person-days, with a flat planning rate of €800 per PD.
SMART OFFICE | CLIENT PROPOSAL
09
Team delivery
436 PD
€348,800
Team reserve
20% labor allowance
€69,760
Team budget
Delivery plus reserve
€418,560
Azure third party
26-week estimate
€876–€2,629
Priced items total
Team budget plus Azure
€419,436–€421,189
Other third-party costs require quotes: agent tools, any extra Microsoft licenses, the real check-in vendor and optional enterprise network or support.
For 200 employees, value depends on verified capacity savings and future office reuse. This range covers priced items only; it is not an all-in ceiling.
Notes: Sources: projects/smart-office-team-cost-estimate.md; projects/smart-office-third-party-cost-estimate.md. Azure translated from USD 1,000-3,000 at 23 Sep 2026 Banque de France reference EUR 1 = USD 1.1411. Excludes tax. If first check-in provider needs hardware, private networking or new licenses, request quotes and reprice at W10. No ROI is asserted without a client baseline.

## Slide 10
Risks, assumptions and next step
A client decision at week 10 controls the full-delivery commitment.
SMART OFFICE | CLIENT PROPOSAL
10
Usage and value
Confirm baseline demand, no-show rate and target economics for the first 200 employees.
Integration choice
Select first check-in provider and notice channel; obtain vendor and license quotes.
Service level
Approve cloud, retention, security, peak load and recovery requirements before sizing.
PoC evidence
Complete the release and outbox work; demonstrate the full no-show journey and record results.
Recommended next step
Agree a joint kickoff and W10 acceptance plan. Commit production scope after verified C1–C3 results and a revised total cost.
Notes: Sources: review/findings-1.txt; projects/smart-office-risks-and-assumptions.md; design/smart-office-hld.md; bid/client-inputs-and-dependencies.md. Release and notification evidence and vendor costs require confirmation before commitment.